## Project Plan and Gantt
CST 8248 - Final Project
Project Name |  | DEE NICE
Project Manager |  | Wendy L., Matt B., Alex B
Project Deliverable |  | A private and public cloud for both a Linux and Windows machine
Start Date |  | 2020-09-21
End Date |  | 2020-11-30
Overall Progress |  | 0%
Please note that all dates on the task are subject to change depending on course schedule and learning.
Private Cloud
ID | Task | Start | End | Column1 | Status
1 | Configure a Jump Server and ensure that it is loaded with appropriate management tools | 2020-09-28 | 2020-10-02 | 4 | Complete
2 | Deploy 2 vSphere hosts | 2020-09-28 | 2020-10-03 | 5
3 | Ensure that the vSphere hosts can connect over the management network | 2020-09-28 | 2020-10-04 | 6 | ASK ISLAM
4 | Deploy the following services on the platform(s) of your choice following best practices: | 2020-10-02 | 2020-10-02 | 0
5 | HTTP | 2020-10-02 | 2020-10-08 | 6
6 | DNS | 2020-10-02 | 2020-10-08 | 6
7 | Active Directory (not LDAP) | 2020-10-04 | 2020-10-08 | 4
8 | iSCSI Target | 2020-10-02 | 2020-10-08 | 6
9 | iSCSi initiator(this needs to be a separate platform from vSphere) | 2020-10-02 | 2020-10-10 | 8
10 | iSCSI - CHAP (Challenge Handshake Authentication Protocol) - Value add | 2020-10-02 | 2020-10-12 | 10
11 | File Server (SMB, NFS, or other) |  |  | 0
12 | Veeam Community Edition(Enterprise Backup) | 2020-10-09 | 2020-10-11 | 2
13 | Spiceworks or similar inventory management system | 2020-10-04 | 2020-10-06 | 2
14 | Windows Admin Center (WAC) (Requires Microsoft Server 2019) | 2020-10-02 | 2020-10-08 | 6
15 | Connect WAC to your Domain using domain admin credentials | 2020-10-02 | 2020-10-08 | 6
16 | Collect inventory information using WAC and Spiceworks | 2020-10-02 | 2020-10-08 | 6
17 | Connect your Veeam Server to vcsa.et.lab using your ET domain credentials | 2020-10-09 | 2020-10-11 | 2
18 | Backup your Web server. | 2020-10-09 | 2020-10-11 | 2
19 | Client Machines should have access to the file shares | 2020-10-09 | 2020-10-11 | 2
20 | vSphere nodes should have separate/dedicated iSCSI LUNS. | 2020-10-02 | 2020-10-12 | 10
21 | Deploy 2 Client Machines. 1 Linux and 1 Windows | 2020-09-28 | 2020-10-02 | 4
22 | Create at least 1 Administrator account and 1 client account | 2020-09-28 | 2020-10-02 | 4
23 | Ensure network connectivity to all devices | 2020-10-19 | 2020-10-24 | 5
24 | Ensure that devices have service connectivity | 2020-10-19 | 2020-10-24 | 5
25 | Use Power CLI to determine the status of machines within your vAppPublic Cloud: | 2020-10-19 | 2020-10-24 | 5
26 | Systems testing and troubleshooting | 2020-10-19 | 2020-11-29 | 41
27 | Reporting, write ups, etc. | 2020-11-26 | 2020-11-29 | 3
28 | Final Report | 2020-09-28 | 2020-11-29 | 62
Public Cloud
Order | Task | Start | End | Duration | Status
| Connect to the Azure interface. (portal.azure.com) | 2020-10-02 | 2020-10-09 | 7
| Establish Governance in public cloud | 2020-10-02 | 2020-10-09 | 7
| Policies | 2020-10-02 | 2020-10-09 | 7
| RBAC | 2020-10-02 | 2020-10-09 | 7
| Deploy a VM in Azure running PostGre SQL | 2020-10-02 | 2020-10-09 | 7
| Create a web server into the Azure cloud. | 2020-10-25 | 2020-11-02 | 8
| Connect your web server to your database VM | 2020-10-25 | 2020-11-02 | 8
| Azure Dashboard for all service | 2020-10-25 | 2020-11-02 | 8
| Secure the communication between the Web front end and the backend by leveraging Network Security Group | 2020-11-02 | 2020-11-09 | 7
| Use PowerShell to determine the status of VM’s within your subscription | 2020-10-25 | 2020-11-02 | 8

## Detailed Task Breakdown
Private Cloud
ID | Task | System | Responsible | Dependancy | Start | End | Column1 | Status
1 | Configure a Jump Server and ensure that it is loaded with appropriate management tools | Remote desktop |  |  | 2020-09-28 | 2020-10-02 | 4 | Complete
2 | Deploy 2 vSphere hosts |  | All | 1 | 2020-09-28 | 2020-10-03 | 5
3 | Ensure that the vSphere hosts can connect over the management network |  | All | 2 | 2020-09-28 | 2020-10-04 | 6 | ASK ISLAM
4 | Deploy the following services on the platform(s) of your choice following best practices: |  |  |  | 2020-10-02 | 2020-10-02 | 0
5 | HTTP | Linux | Matthew | 1 | 2020-10-02 | 2020-10-08 | 6
6 | DNS | Linux | Matthew | 1 | 2020-10-02 | 2020-10-08 | 6
7 | Active Directory (not LDAP) | Windows | Matthew | 1 | 2020-10-04 | 2020-10-08 | 4
8 | iSCSI Target | Windows (With Veeam) | Wendy | 1 | 2020-10-02 | 2020-10-08 | 6
9 | iSCSi initiator(this needs to be a separate platform from vSphere) | Windows (with veeam) | Wendy | 1 | 2020-10-02 | 2020-10-10 | 8
10 | iSCSI - CHAP (Challenge Handshake Authentication Protocol) - Value add |  | Wendy | 1 | 2020-10-02 | 2020-10-12 | 10
11 | File Server (SMB, NFS, or other) | Windows (With Veeam) | Alex | 7 |  |  | 0
12 | Veeam Community Edition(Enterprise Backup) | Windows (With Veeam) | Alex | 11 | 2020-10-09 | 2020-10-11 | 2
13 | Spiceworks or similar inventory management system | Windows | Matthew |  | 2020-10-04 | 2020-10-06 | 2
14 | Windows Admin Center (WAC) (Requires Microsoft Server 2019) | Windows | Wendy | 7 | 2020-10-02 | 2020-10-08 | 6
15 | Connect WAC to your Domain using domain admin credentials | Windows | All | 14 | 2020-10-02 | 2020-10-08 | 6
16 | Collect inventory information using WAC and Spiceworks | Windows | Matthew |  | 2020-10-02 | 2020-10-08 | 6
17 | Connect your Veeam Server to vcsa.et.lab using your ET domain credentials | Windows | Alex | 12 | 2020-10-09 | 2020-10-11 | 2
18 | Backup your Web server. | Windows (With Veem) | Alex | 12 | 2020-10-09 | 2020-10-11 | 2
19 | Client Machines should have access to the file shares | Windows (With Veem) | Alex | 12 | 2020-10-09 | 2020-10-11 | 2
20 | vSphere nodes should have separate/dedicated iSCSI LUNS. | Windows (With Veem) | Wendy | 1 | 2020-10-02 | 2020-10-12 | 10
21 | Deploy 2 Client Machines. 1 Linux and 1 Windows | Linux and Windows | Wendy | 2 | 2020-09-28 | 2020-10-02 | 4
22 | Create at least 1 Administrator account and 1 client account | Linux and Windows | Wendy | 21 | 2020-09-28 | 2020-10-02 | 4
23 | Ensure network connectivity to all devices | Linux and Windows | Alex | 22 | 2020-10-19 | 2020-10-24 | 5
24 | Ensure that devices have service connectivity | Linux and Windows | Alex | 22 | 2020-10-19 | 2020-10-24 | 5
25 | Use Power CLI to determine the status of machines within your vAppPublic Cloud: | Linux and Windows | Alex | 22 | 2020-10-19 | 2020-10-24 | 5
26 | Systems testing and troubleshooting |  | All |  | 2020-11-26 | 2020-11-29 | 3
27 | Reporting, write ups, etc. | MS Word | Wendy | 1-25 | 2020-11-26 | 2020-11-29 | 3
28 | Final Report |  | Wendy | 27 | 2020-09-28 | 2020-11-29 | 62
Public Cloud
Order | Task | System | Responsible |  | Start | End |  | Status
| Connect to the Azure interface. (portal.azure.com) | Windows | All |  | 2020-10-02 | 2020-10-09 | 7
| Establish Governance in public cloud | Windows | Matthew |  | 2020-10-02 | 2020-10-09 | 7
| Policies | windows | Matthew |  | 2020-10-02 | 2020-10-09 | 7
| RBAC | windows | Matthew |  | 2020-10-02 | 2020-10-09 | 7
| Deploy a VM in Azure running PostGre SQL | windows | Matthew |  | 2020-10-02 | 2020-10-09 | 7
| Create a web server into the Azure cloud. | windows | Alex |  | 2020-10-25 | 2020-11-02 | 8
| Connect your web server to your database VM | windows | Wendy |  | 2020-10-25 | 2020-11-02 | 8
| Azure Dashboard for all service | windows | Alex |  | 2020-10-25 | 2020-11-02 | 8
| Secure the communication between the Web front end and the backend by leveraging Network Security Group | windows | Wendy |  | 2020-11-02 | 2020-11-09 | 7
| Use PowerShell to determine the status of VM’s within your subscription | windows | Alex |  | 2020-10-25 | 2020-11-02 | 8

## Meeting minutes
This tab will highlight the team meetings, summary of notes, the attendance and what the next steps are.
Date | In Attendance | Summary | Next steps
2020-09-21 | -Alex -Wendy -Matt | Started Assignment 1, created a communications and project plan. Met together on MS Teams. | - Decide on dates for the tasks breakdown - Set date for weekly meetings - Review documents - Save document onto GitHub
2020-09-22 | - Wendy - Matt - Alex | - Discuss the project plan - Setting dates and times - Organized CLI - week by week - Logged into Remote desktop - Discussed the planning for project - Review and put together virtual Machine | - Breakdown week by week plan using CLI - Next meeting: Sunday 27th, 10am - Wendy to change password - Alex and Matt to update task and project plan - Wendy to add documentation to Github - Alex to ask Islam for clarification
2020-09-27 | - Wendy - Matt - Alex | - set responsibilities for each member | - Wendy to ask Islam to demo the vSphere download

## Stakeholders
This document will record the minutes and details of any meetings we have with stakeholders
Date | Stakeholder | Responsible Contact | Question | Answer/Details | Status
2020-09-21 | Islam | Someone in Class 23 | How do we upload our assignments? | Through Github. Ensure to download Git and start a repo | Resolved
2020-09-22 | Islam/Denis | Alexander Barstow | How are the cloud systems supposed to be set up? Is public cloud on the one machine? | public/private - reaching out to use azure structure via public cloud - will have services running in private cloud (infrastructure hosted at AC), 1 virtual machine and 1 HTTP webpage rnuning on public cloud running on the azure infrastructure - PS structure looking at subscription and health report - can also make dashboard to look at different public services | REsolved
2020-09-28 | Islam/Denis | Wendy Liao | - Wendy to ask Islam to demo the vSphere download

## Communication plan
Communications plan
Communication Type | Devlierable | Description | Delivery Method | Frequency | Owner | Audience
Meetings | Meeting on MS teams | Check in on status of all the deliverables | Virtual on MS Teams | Once a week | Wendy L | N/A project team
DNS Demo | Meeting on MS teams | Demo running DNS to team | Virtual on MS Teams | Once |  | N/A project team
AD Demo | Meeting on MS teams | Demo running AD to team | Virtual on MS Teams | Once |  | N/A project team
HTTP | Meeting on MS teams | Demo running http to team | Virtual on MS Teams | Once |  | N/A project team
LDAP or Active Directory | Meeting on MS teams | Demo running LDAP/AD to team | Virtual on MS Teams | Once |  | N/A project team
iSCSI Target | Meeting on MS teams | Demo running iSCSI to team | Virtual on MS Teams | Once |  | N/A project team
iSCSi initiator(this needs to be a separate platform from vSphere) | Meeting on MS teams | Demo running iSCSI to team | Virtual on MS Teams | Once |  | N/A project team
File Server (SMB, NFS, or other) | Meeting on MS teams | Demo running File Server to team | Virtual on MS Teams | Once |  | N/A project team
Veeam Community Edition(Enterprise Backup) | Meeting on MS teams | Demo running Veeam to team | Virtual on MS Teams | Once |  | N/A project team
Spiceworks or similar inventory management system | Meeting on MS teams | Demo running Spiceworks to team | Virtual on MS Teams | Once |  | N/A project team
Windows Admin Center (WAC) (Requires Microsoft Server 2019) | Meeting on MS teams | Demo running WAC to team | Virtual on MS Teams | Once |  | N/A project team
Demo entire project | Meeting on MS teams | Demo the two systems working to the professors | Virtual on MS Teams | Once |  | N/A project team

## COMPLETE - Schedule
Monday | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 20:00 | 21:00 | 22:00
Wendy | [12 empty] | Emerging Tech class |  |  |  | Busy
Alex | [16 empty] | Flexible (can change plans)
Matt | [12 empty] | Emerging Tech class |  |  |  | Free
Alex's recs
Tuesday | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 20:00 | 21:00 | 22:00
Wendy
Alex | [15 empty] | Options: | Monday 17H-20H
Matt | [16 empty] | Tuesday 17H-20H
Wednesday 17H-18H
Wednesday | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 20:00 | 21:00 | 22:00 |  | Thursday 17H-18H
Wendy | [16 empty] | Sunday 8-12. 18H-22H
Alex
Matt
Thursday | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 20:00 | 21:00 | 22:00
Wendy
Alex
Matt
Friday | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 20:00 | 21:00 | 22:00
Wendy
Alex
Matt
Saturday | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 20:00 | 21:00 | 22:00
Wendy
Alex
Matt | [6 empty] | Every | Other | Week
Sunday | 8:00 | 9:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | 20:00 | 21:00 | 22:00
Wendy
Alex
Matt